## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARANDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000366/2024-2025 | 1450/ED | 25/07/2024 | 23/10/2024 | MOITRA ENGINEERING CO. | 11.08 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SAIDPUR ZONE-II (1No.), SAIDPUR ZONE-I (2Nos.) ARANDI (1 No.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000224/2024-2025 | 3435/HUG | 03/10/2024 | 01/01/2025 | T.K. INTERNATIONAL | 47.2 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ARANDI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000451/2024-2025 | 4080/HUG | 19/12/2024 | 19/03/2025 | SRI KRISHNA ENTERPRISE | 17.15 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site at ARANDI , BATANOL Zone-I , GOPALBATI W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000426/2024-2025 | 3667/HUG | 13/11/2024 | 28/12/2024 | DEV AND COMPANY | 31.66 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ARANDI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000116/2023-2024 | 1445/HUG | 18/05/2023 | 23/03/2025 | SAKSHI ENTERPRISE | 11.81 | 0 | 0 | 40
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Restoration of damaged pipe line of Arandi water supply scheme due to construction of drain by Arandi-I G.P. under Arambagh Sub-Division, P.H.E. Dte. (PART-A) [Block-Arambagh] | Assistant Engineer |  | ORD/001479/2023-2024 | 287/Arg | 14/03/2024 | 29/03/2024 | TITAS CONSTRUCTION | 0.96 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Restoration of damaged pipe line of Arandi water supply scheme due to construction of drain by Arandi-I G.P. under Arambagh Sub-Division, P.H.E. Dte. (PART-B) [Block-Arambagh] | Assistant Engineer |  | ORD/001480/2023-2024 | 288/Arg | 14/03/2024 | 29/03/2024 | TITAS CONSTRUCTION | 0.84 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Arandi water supply scheme, T.W. No. III, Block: Arambag, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/002101/2022-2023 | 1919/ED | 21/11/2022 | 29/03/2025 | INDTECH ASSOCIATES. | 10.67 | 2.8 | 26.29 | 30
9 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) AMDOBA PWSS (ii) BADANGANJ PWSS (iii) HAZIPUR PWSS (iv) ARANDI PWSS (v) MAYAPUR PWSS (vi) BULUNDI PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000432/2024-2025 | 799/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 132.32 | 2.8 | 2.12