## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ARANDI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000116/2023-2024 | 1445/HUG | 18/05/2023 | 17/06/2023 | SAKSHI ENTERPRISE | 11.81 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Arandi water supply scheme, T.W. No. III, Block: Arambag, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002101/2022-2023 | 1919/ED | 21/11/2022 | 19/02/2023 | INDTECH ASSOCIATES. | 10.67 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | SM/16124 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARANDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000366/2024-2025 | 1450/ED | 25/07/2024 | 23/10/2024 | MOITRA ENGINEERING CO. | 11.08 | 0 | 0 | 0
Total | [13 empty] | 33.56 | 0 | 0