## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Supply, delivery & installation of automatic Chlorinator for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002115/2022-2023 | 70/HMSD | 10/01/2023 | 17/01/2023 | BISALAXMI ENTERPRISE | 0.8 | 0.8 | 100 | 100
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Providing 770 nos Functional Household Tap Connection (FHTC) within the command area of DIHIBAGNAN Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 385 Nos FHTC out of 770 Nos FHTC within the command area of DIHIBAGNAN Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 1599635.50 (50% of Rs. 3199271.00) | Assistant Engineer |  | ORD/000598/2021-2022 | 2231/HUG | 15/12/2021 | 14/01/2022 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 12.8 | 12.09 | 94.47 | 95
3 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Hiring of diesel driven contract carriage along with driver for the official use of the SEMC-I PHED |  |  | ORD/000962/2023-2024 | 933_HMSD | 18/04/2023 | 17/04/2024 | S.P. CONSTRUCTION | 5 | 1.58 | 31.66 | 30
4 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002116/2022-2023 | 657/HMSD | 04/04/2022 | 19/04/2022 | BOSE & CHATTERJEE INDUSTRIES | 2.37 | 1.18 | 50 | 30
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Providing 840 nos Functional Household Tap Connection (FHTC) within the command area of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer |  | ORD/000599/2021-2022 | 1915/HUG | 27/10/2021 | 06/12/2021 | M/S PRADYUT KUMAR HAZRA | 40.43 | 2.5 | 6.17 | 97
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Providing 1700 nos F.H.T.C. in Dihibagnan, Para Bagnan & Bhabanipur village of Dihibagnan and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer |  | ORD/000918/2020-2021 | 1687/Hug | 17/12/2020 | 26/01/2021 | M/S PRADYUT KUMAR HAZRA | 79.86 | 2.57 | 3.22 | 97
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Laying CI/DI pipes & specials for rising main pipe line in between T.W No.- III to O.H.R. and interconnection with distribution system at 3rd Tube Well Site of DIHI BAGNAN W/S Scheme under Arambagh Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000520/2021-2022 | 176/Arg | 21/03/2022 | 31/03/2022 | M/S ROY ENTERPRISE | 4.83 | 3.72 | 77.19 | 100
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Belmuri village under Dhaniakhali Block, Jot Haranda village of Dhnaiakhali Block and Radhaballavpur village of Dhaniakhali Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000985/2023-2024 | 259/CH | 14/03/2024 | 21/03/2024 | R.K. TRADERS | 0.95 | 0.48 | 50 | 100
9 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dihi Bagnan water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001476/2021-2022 | 552/ED | 22/03/2022 | 20/06/2022 | BISALAXMI ENTERPRISE | 6.59 | 6.14 | 93.16 | 30
10 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | SM/16130 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DIHI BAGNAN PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000368/2024-2025 | 1452/ED | 25/07/2024 | 23/10/2024 | BARMAN ROY TRADERS | 11.09 | 0 | 0 | 0
Total | [13 empty] | 164.72 | 31.06 | 18.86