## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | SM/16136 | New | Material Requisition To Resource Division |  |  | RTOR000290/2023-2024 | 1383/36/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 3.33 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Electrical | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | SM/16136 | New | Quotation Bill for New Service Connection at Rajballavbati W/S. Sch. TW-I |  |  | BILL/04221/2023-2024 | 412 | 09/11/2023 | 09/11/2023 | WBSEDCL | 6.55 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Electrical | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | SM/16136 | New | Quotation for new service connection charge at Rajballabhbati PWSS, TW - II |  |  | BILL/04485/2023-2024 | 528 | 15/12/2023 | 15/12/2023 | WBSEDCL | 1.71 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | SM/16136 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) |  | ORD/000765/2023-2024 | 149/Chan | 16/02/2024 | 02/03/2024 | TECHVISION | 0.84 | 0.84 | 100 | 98
5 | HOOGHLY | Haripal | Electrical | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | SM/16136 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajaballabhbati water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000033/2023-2024 | 1710/ED | 18/04/2023 | 01/04/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.5 | 16.76 | 81.76 | 20
Total | [13 empty] | 32.93 | 17.6 | 53.46