## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-II) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000024/2023-2024 | 1701/ED | 18/04/2023 | 17/07/2023 | DEBJYOTI BASU | 20.5 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Material Requisition To Resource Division |  |  | RTOR000300/2023-2024 | 1383/44/Hug | 15/05/2023 |  | Resource Division | 3.76 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Quotation of New Service Connection Charge for Mahishtikri w/s Scheme,Zone-2,TW No-I Block-Haripal Dist-Hooghly under ED,PHE Dte |  |  | BILL/03761/2023-2024 | 264 | 07/09/2023 |  | WBSEDCL | 9.89 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Quotation of New Service Connection for Mahistikri w/s Scheme,Zone-2,TW No-2 Block-Haripal,Dist-Hooghly under ED,PHE Dte |  |  | BILL/03762/2023-2024 | 263 | 07/09/2023 |  | WBSEDCL | 3.24 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Material Requisition To Resource Division |  |  | RTOR000453/2023-2024 | 3058/18/Hug | 11/10/2023 |  | Resource Division | 3.76 | 0 | 0 | 0
7 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Maheshtikri Zone 2 PWSS under Chandannagar Sub-Division Phe Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000932/2023-2024 | 278/Chan | 15/03/2024 | 30/03/2024 | SUDIPTA SINHA | 0.88 | 0.42 | 48.04 | 100
8 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | MAHISHTIKRI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000170/2023-2024 | 1658/HUG | 07/06/2023 | 05/09/2023 | BIMAL KUMAR HALDER | 199.05 | 70.21 | 35.27 | 70
9 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16138 | New | Horizontal Auger boring with water jet system Including Approach road with culvert at MAHISHTIKRI (ZONE-I & ZONE-II) under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Haripal Block junior Enginner | ORD/000028/2024-2025 | 2285/HUG | 14/06/2024 | 14/07/2024 | MAA TARA CONSTRUCTION | 4.82 | 0 | 0 | 0
Total | [13 empty] | 317.07 | 70.63 | 22.28