## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000312/2022-2023 | 1242/ED | 06/03/2023 | 25/11/2024 | ORIENTAL ENGINEERING CO. | 40.49 | 20.23 | 49.97 | 80
2 | HOOGHLY | Singur | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | BIGHATI (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000099/2023-2024 | 1374/HUG | 15/05/2023 | 31/03/2025 | S & P ENTERPRISE | 531.25 | 478.44 | 90.06 | 100
3 | HOOGHLY | Singur | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1235/4/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 34.06 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Quotation Bill for New Service Connection at Bighati W/S. Sch. TW-I, Z-II |  |  | BILL/04242/2023-2024 | 423 | 10/11/2023 | 10/11/2023 | WBSEDCL | 5.25 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Quotation for new service connection at Bighati W/s Scheme, Zone - I, T/W - I |  |  | BILL/04124/2023-2024 | 380 | 25/10/2023 | 25/10/2023 | WBSEDCL | 3.78 | 0 | 0 | 0
6 | HOOGHLY | Singur | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Quotation for new service connection at Bighati w/s sch. (Zone - I), T/W -II, dt. - Hooghly |  |  | BILL/03626/2023-2024 | 223 | 28/08/2023 | 28/08/2023 | WBSEDCL | 5.21 | 0 | 0 | 0
7 | HOOGHLY | Singur | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Restoration work for the damages Chandannagar Nasibpur Road to Vhadreswar Station road |  |  | BILL/01130/2023-2024 | BP-2023-24-853 | 21/02/2024 | 21/02/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 43.24 | 0 | 0 | 0
8 | HOOGHLY | Singur | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Repairing potholes and mending depressions by Jhama Metal Consolidation and cutting kutchha drain at different Road under Singur -I GP under singur Block under Chandannagar Sub Division PHE DTE | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000300/2025-2026 | 933/CHAN | 21/07/2025 | 10/08/2025 | M/S BISWAS CONSTRUCTION | 4.92 | 0 | 0 | 100
9 | HOOGHLY | Singur | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/16236 | New | Repairing potholes and mending depressions by Jhama Metal Consolidation and cutting kutchha drain at different Road under Singur -II GP under singur Block under Chandannagar Sub Division PHE DTE | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000301/2025-2026 | 934/CHAN | 21/07/2025 | 10/08/2025 | M/S BISWAS CONSTRUCTION | 4.91 | 0 | 0 | 100
Total | [13 empty] | 673.1 | 498.67 | 74.09