## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of GOBINDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000338/2021-2022 | 15/Hug | 04/01/2022 | 03/02/2022 | SWASTIK ENTERPRISE | 14.91 | 14.8 | 99.25 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 1385/42/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.39 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Quotation Bill for for New Service Connection at Gobindopur W/S. Sch. |  |  | BILL/04319/2023-2024 | 427 | 17/11/2023 | 17/11/2023 | WBSEDCL | 4.41 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 12/08/2023 | SPG ENTERPRISES | 48.51 | 0 | 0 | 70
5 | HOOGHLY |  | Electrical | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No. II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002487/2023-2024 | 138/ED | 16/01/2024 | 15/04/2024 | MUKHERJEE ART CENTRE | 10.7 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Renovation Work of R.C.C. Elevated Reservoir of GOBINDAPUR PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. |  |  | ORD/000681/2025-2026 | 2370/HUG | 10/09/2025 | 09/12/2025 | M/S BIMAL DAS AND CO. | 10.05 | 0 | 0 | 0
Total | [13 empty] | 89.97 | 14.8 | 16.45