## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of GOBINDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000338/2021-2022 | 15/Hug | 04/01/2022 | 03/02/2022 | SWASTIK ENTERPRISE | 14.91 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 1385/42/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.39 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Quotation Bill for for New Service Connection at Gobindopur W/S. Sch. |  |  | BILL/04319/2023-2024 | 427 | 17/11/2023 | 17/11/2023 | WBSEDCL | 4.41 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 12/08/2023 | SPG ENTERPRISES | 48.51 | 0 | 0 | 70
5 | HOOGHLY |  | Electrical | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No. II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002487/2023-2024 | 138/ED | 16/01/2024 | 15/04/2024 | MUKHERJEE ART CENTRE | 10.7 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Renovation Work of R.C.C. Elevated Reservoir of GOBINDAPUR PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. |  |  | ORD/000681/2025-2026 | 2370/HUG | 10/09/2025 | 09/12/2025 | M/S BIMAL DAS AND CO. | 10.05 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Augmentation of GOBINDAPUR Piped Water Supply Scheme with Sinking of tube-well, Laying Distribution System, Providing FHTC, construction of switch-room & boundary wall & Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, under Arambag Sub-Division of Hooghly Division PHE Dte. within KHANAKUL-I Block, District:- Hooghly. | Assistant Engineer | Junior Engineer (Civill) | ORD/000062/2023-2024 | 1270/HUG | 03/05/2023 | 25/07/2025 | CREATION CONSTRUCTION | 206.77 | 0 | 0 | 100
8 | HOOGHLY |  | Electrical | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000055/2023-2024 | 1799/ED | 24/04/2023 | 02/09/2025 | OSMAN SEKH | 10.75 | 0 | 0 | 50
9 | HOOGHLY |  | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme | SM/16351 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PATUL PWSS (ii) GHOSHPUR PWSS (iii) UDNA PWSS (iv) POLE PWSS (v) GOBINDAPUR PWSS (vi) THAKURANICHAK PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000436/2024-2025 | 800/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 308.44 | 0 | 0