## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KRISHNARAMPUR W/S SCH, CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000378/2022-2023 | 1999/CDD | 08/02/2023 | 10/03/2023 | UNIVERSAL ENTERPRISES | 12.65 | 11 | 86.93 | 0
2 | HOOGHLY |  | Hooghly Division | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000325/2023-2024 | 1384/21/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 8.93 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Quotation bill for new service connection at Krishnarampur W/S. Sch. PH-III |  |  | BILL/00726/2023-2024 | 31 | 12/05/2023 | 12/05/2023 | WBSEDCL | 2.37 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | New service connection charges for Krishnarampur w/s scheme, PH No.-III |  |  | BILL/01161/2023-2024 | 86 | 12/07/2023 | 12/07/2023 | WBSEDCL | 2.37 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system with FHTC of KRISHNARAMPUR W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000044/2023-2024 | 1172/HUG | 20/04/2023 | 04/06/2023 | TAPAS ADHYA | 63.38 | 51.97 | 81.99 | 35
6 | HOOGHLY |  | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Quotation bill for new service connection charges at Krishnarampur PWSS P.H. No.-IV, Hooghly. Application No. 5004062824 Ref ID: 503597308 |  |  | BILL/00117/2024-2025 | 43 | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.42 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNARAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000174/2024-2025 | 1198/ED | 14/06/2024 | 02/05/2025 | P.P. CONCERN | 10.75 | 0 | 0 | 75
8 | HOOGHLY |  | Hooghly Division | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Estimate for Construction of boundary wall, Internal Pathway and allied works at 3rd TW Site of Krishnarampur Water Supply Scheme under Serampore sub Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001292/2024-2025 | 64/SER | 20/01/2025 | 27/01/2025 | SURAJIT SINGHA RAY | 4.42 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | SM/16447 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnarampur water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000019/2023-2024 | 1635/ED | 11/04/2023 | 01/06/2026 | D.S. ENTERPRISE | 11.41 | 11.13 | 97.55 | 70
Total | [13 empty] | 119.7 | 74.1 | 61.9