## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Borhal W/S Scheme (Z-I), Jangipara block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000457/2022-2023 | 2330/CDD | 30/03/2023 | 29/04/2023 | C.M. ENTERPRISE | 22.68 | 0 | 0 | 47
2 | HOOGHLY |  | Central Drilling | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 180 mtrs. Depth) by utilising Departmental machineries for Borhal W/S Scheme (Z-I, TW-I), Jangipara block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000458/2022-2023 | 1995/CDD | 07/02/2023 | 09/03/2023 | UTTAM KUMAR CHATTERJEE | 12.54 | 0 | 0 | 100
3 | HOOGHLY |  | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Borhal Z-I P H NO-3 |  |  | BILL/02294/2023-2024 | 145 | 26/07/2023 | 26/07/2023 | WBSEDCL | 4.55 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-I) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000015/2023-2024 | 1631/ED | 11/04/2023 | 10/07/2023 | S.S. ENTERPRISES | 23.3 | 0 | 0 | 85
5 | HOOGHLY |  | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MORHAL PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002882/2023-2024 | 457/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 0 | 0 | 65
6 | HOOGHLY |  | Hooghly Division | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Development of BORHAL (ZONE-I)W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000111/2023-2024 | 1440/HUG | 18/05/2023 | 02/07/2023 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 31.23 | 0 | 0 | 25
7 | HOOGHLY |  | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Quotation money deposition for new service connection at Borhal w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004065635 Reference ID- 503592946 SM Code- 16449 |  |  | BILL/00487/2024-2025 | 146 | 22/05/2024 | 22/05/2024 | WBSEDCL | 4.57 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002466/2023-2024 | 327/ED | 21/02/2024 | 12/06/2026 | DEY ENTERPRISE | 20.85 | 0 | 0 | 45
9 | HOOGHLY |  | Hooghly Division | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Estimate of development at 3rd T/W site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/001260/2024-2025 | 60/SER | 20/01/2025 | 27/01/2025 | SURAJIT SINGHA RAY | 3.5 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | SM/16449 | Augmentation | Estimate of Development of 4th T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/001261/2024-2025 | 61/SER | 20/01/2025 | 27/01/2025 | SURAJIT SINGHA RAY | 2.75 | 0 | 0 | 0
Total | [13 empty] | 135.67 | 0 | 0