## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | SM/16450 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL (Z-II, TW-I) JANGIPARA BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000412/2022-2023 | 2003/CDD | 09/02/2023 | 11/03/2023 | UTTAM KUMAR CHATTERJEE | 12.54 | 10.75 | 85.73 | 0
2 | HOOGHLY |  | Central Drilling | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | SM/16450 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL (Z-II) PWSS (TW-I), JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000374/2022-2023 | 1774/CDD | 02/01/2023 | 01/02/2023 | C.M. ENTERPRISE | 12.52 | 11.06 | 88.35 | 0
3 | HOOGHLY |  | Central Drilling | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | SM/16450 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL W/S SCH (ZONE-II) (TW-II), JANGIPARA BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000383/2022-2023 | 1994/CDD | 07/02/2023 | 09/03/2023 | CHANDA ENTERPRISE | 25.08 | 22.93 | 91.41 | 100
4 | HOOGHLY |  | Hooghly Division | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | SM/16450 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 1384/4/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.62 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | SM/16450 | Augmentation | Quotation Bill for New Service Connection at Borhal W/S. Sch. PH-2 & 3 |  |  | BILL/00001/2023-2024 | 26 | 11/05/2023 | 11/05/2023 | WBSEDCL | 11.8 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | SM/16450 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-II) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000983/2023-2024 | 1632/ED | 11/04/2023 | 10/07/2023 | INDTECH ASSOCIATES. | 22.81 | 22.17 | 97.21 | 85
Total | [13 empty] | 85.37 | 66.92 | 78.39