## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Sinking of tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of KULTEGHORI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000381/2023-2024 | 2516/HUG | 18/08/2023 | 16/03/2026 | SHREE JAGANNATH ENTERPRISE | 32.57 | 1.95 | 6 | 40
2 | HOOGHLY |  | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 10/08/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 0 | 0 | 100
3 | HOOGHLY |  | Electrical | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kulteghori (Aug.) water supply scheme, T.W. No. I, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000077/2023-2024 | 1933/ED | 15/05/2023 | 01/06/2026 | DAS ENTERPRISE | 11.48 | 0 | 0 | 30
4 | HOOGHLY |  | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 1383/39/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.33 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Quotation money deposition for new service connection at Kulteghori w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004314314 Reference ID- 503702908 SM Code- 16564 |  |  | BILL/01407/2024-2025 | 349 | 31/07/2024 | 31/07/2024 | WBSEDCL | 24.36 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Installation of sluice valve for Kultegori W/S Scheme under chandannagar Sub - Division, PHE Dte. (Part - A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000383/2025-2026 | 1031/Chan | 31/07/2025 | 07/08/2025 | M/S RAJKUMAR KHAN | 0.94 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme | SM/16564 | Augmentation | Installation of sluice valve for Kultegori W/S Scheme under chandannagar Sub - Division, PHE Dte. (Part - B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000385/2025-2026 | 1032/Chan | 31/07/2025 | 07/08/2025 | M/S RAJKUMAR KHAN | 0.71 | 0 | 0 | 100
Total | [13 empty] | 150.84 | 1.95 | 1.3