## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Construction of 1 (One) No. Pump House (3.0 x 3.6 m ) with additional plinth height including internal pathway at 6th tubewell site of Bandipur PWSS Scheme under Hooghly Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000765/2022-2023 | 145/Chan | 16/03/2023 | 25/04/2023 | BMR ENGINEERING & CONSTRUCTION | 4.99 | 3.25 | 65.21 | 80
2 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of boundary wall at 2nd TW site of Bandipur Piped Water Supply Scheme Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000947/2023-2024 | 286/Chan | 15/03/2024 | 30/03/2024 | SHREE JAGANNATH ENTERPRISE | 0.99 | 0.99 | 99.25 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing Damaged pipeline at Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000954/2023-2024 | 292/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.37 | 0.37 | 99.87 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Laying of Rising main for Interconnection of Laying distribution system at 6th Tube well site of Bandipur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000949/2023-2024 | 287/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.92 | 0.89 | 96.82 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of pump house at 2nd TW site of Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000946/2023-2024 | 285/Chan | 15/03/2024 | 30/03/2024 | SHREE JAGANNATH ENTERPRISE | 1 | 0.97 | 97.86 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in left out portion of BANDIPUR PWSS, Block. HARIPAL under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000042/2023-2024 | 1171/HUG | 20/04/2023 | 02/10/2024 | TITAS CONSTRUCTION | 57.96 | 31.61 | 54.54 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Supply fitting fixing of 4 nos. 100 mm dia Sluice Valve for proper distribution of water at Bandipur Water Supply Scheme in Haripal Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000277/2024-2025 | 930/Chan | 05/11/2024 | 20/11/2024 | AYUSH ENTERPRISE | 0.89 | 0.89 | 100 | 100
8 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Supplying fitting fixing of 2 nos. 100 mm. dia. Sluice Valve for proper distribution of water at Bandipur Water Supply Scheme in Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000278/2024-2025 | 931/Chan | 05/11/2024 | 20/11/2024 | AYUSH ENTERPRISE | 0.45 | 0.45 | 100 | 100
9 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Bandipur W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000235/2025-2026 | 885/CHAN | 21/07/2025 | 10/08/2025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.97 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Road restoration at Bandipur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000195/2025-2026 | 843/CHAN | 21/07/2025 | 10/08/2025 | R.K. TRADERS | 4.92 | 0 | 0 | 50
11 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Road restoration at Bandipur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000194/2025-2026 | 842/CHAN | 21/07/2025 | 10/08/2025 | JOY GURU ENTERPRISE | 4.84 | 0 | 0 | 50
12 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Boundary fencing work at Bandipur PWSS under Chandannagar Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000242/2025-2026 | 892/CHAN | 21/07/2025 | 05/08/2025 | JOY GURU ENTERPRISE | 3.61 | 0 | 0 | 50
Total | [13 empty] | 85.92 | 39.43 | 45.89