## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Construction of 1 (One) No. Pump House (3.0 x 3.6 m ) with additional plinth height including internal pathway at 6th tubewell site of Bandipur PWSS Scheme under Hooghly Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000765/2022-2023 | 145/Chan | 16/03/2023 | 25/04/2023 | BMR ENGINEERING & CONSTRUCTION | 4.99 | 0 | 0 | 80
2 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of boundary wall at 2nd TW site of Bandipur Piped Water Supply Scheme Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000947/2023-2024 | 286/Chan | 15/03/2024 | 30/03/2024 | SHREE JAGANNATH ENTERPRISE | 0.99 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing Damaged pipeline at Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000954/2023-2024 | 292/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.37 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Laying of Rising main for Interconnection of Laying distribution system at 6th Tube well site of Bandipur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000949/2023-2024 | 287/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.92 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of pump house at 2nd TW site of Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000946/2023-2024 | 285/Chan | 15/03/2024 | 30/03/2024 | SHREE JAGANNATH ENTERPRISE | 1 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of damaged FHTC connection at Bandipur PWSS under Chandannagar Sub-Division under Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002195/2024-2025 | 152/Chan | 31/01/2025 | 15/02/2025 | MS CHANDIMATA CONSTRUCTION | 0.91 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in left out portion of BANDIPUR PWSS, Block. HARIPAL under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000042/2023-2024 | 1171/HUG | 20/04/2023 | 02/10/2024 | TITAS CONSTRUCTION | 57.96 | 0 | 0 | 100
Total | [13 empty] | 67.14 | 0 | 0