## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | SM/16651 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1235/10/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 15.57 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | SM/16651 | New | Material Requisition To Resource Division |  |  | RTOR000401/2023-2024 | 3058/16/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 8.67 | 0 | 0 | 0
3 | HOOGHLY | Singur | Electrical | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | SM/16651 | New | Quotation for new service connection at Ganderpukur W/S Sch. , T/W No. - II, Block- Singur, Dt. - Hooghly |  |  | BILL/04075/2023-2024 | 347 | 11/10/2023 | 11/10/2023 | WBSEDCL | 2.39 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | SM/16651 | New | Quotation for new service connection at Ganderpukur W/S Sch., T/W No. - I, Block - Singur, Dt. - Hooghly |  |  | BILL/04074/2023-2024 | 339 | 10/10/2023 | 10/10/2023 | WBSEDCL | 0.64 | 0 | 0 | 0
5 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | SM/16651 | New | GANDERPUKUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division Block-SINGUR, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000176/2023-2024 | 1681/HUG | 08/06/2023 | 01/04/2026 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 357.8 | 201.4 | 56.29 | 85
6 | HOOGHLY | Singur | Electrical | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | SM/16651 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ganderpukur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000041/2023-2024 | 1727/ED | 19/04/2023 | 18/07/2023 | M/S DAS ENTERPRISE | 21.05 | 20.98 | 99.64 | 49
Total | [13 empty] | 406.11 | 222.37 | 54.76