## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Hooghly Division | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 1385/34/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 6.52 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Hooghly Division | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Material Requisition To Resource Division |  |  | RTOR000422/2023-2024 | 3057/39/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 6.52 | 0 | 0 | 0
3 | HOOGHLY | Goghat-I | Hooghly Division | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1234/21/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 19.42 | 0 | 0 | 0
4 | HOOGHLY | Goghat-I | Electrical | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Quotation Bill for New Service Connection at Gopalbati W/S. Sch. |  |  | BILL/04409/2023-2024 | 487 | 06/12/2023 | 06/12/2023 | WBSEDCL | 3.95 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Electrical | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Quotation of New Service Connection for Gopalbati w/s Scheme,PH No-II,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/16756) Application No-5004475080 Reference Id-503799042 |  |  | BILL/02474/2024-2025 | 618 | 05/12/2024 | 05/12/2024 | WBSEDCL | 4.72 | 0 | 0 | 0
6 | HOOGHLY | Goghat-I | Electrical | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gopalbati water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer4 | ORD/000056/2023-2024 | 1800/ED | 24/04/2023 | 01/04/2025 | KAMAKHYA ENTERPRISE | 20.26 | 0 | 0 | 30
7 | HOOGHLY | Goghat-I | Hooghly Division | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | GOPALBATI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000138/2023-2024 | 1491/HUG | 22/05/2023 | 01/01/2026 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 339.91 | 0 | 0 | 30
8 | HOOGHLY | Goghat-I | Hooghly Division | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Additional works for Laying Distribution main by HDD process at Gopalbati and Gobindanagar Zone II W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000311/2024-2025 | 3687/HUG | 14/11/2024 | 11/10/2025 | MS PRADIP KUMAR PAL | 14.33 | 0 | 0 | 0
9 | HOOGHLY | Goghat-I | Hooghly Division | Gopalbati Piped Water Supply Scheme. | SM/16756 | New | Laying of Additional Pipeline for GOPALBATI Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh. | Assistant Engineer | Junior Engineer (Civill) | ORD/000229/2024-2025 | 3431/HUG | 03/10/2024 | 03/04/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 23.25 | 0 | 0 | 15
Total | [13 empty] | 438.88 | 0 | 0