## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Material Requisition To Resource Division |  |  | RTOR000432/2023-2024 | 3057/34/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.7 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1234/19/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 27.39 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Material Requisition To Resource Division |  |  | RTOR000328/2023-2024 | 2607/1/Hug | 29/08/2023 | 29/08/2023 | Resource Division | 14.19 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Quotation for New Service Connection of Ramnagar W/s scheme, PH No-I, District-Hooghly under Electrical Division, PHE Dte |  |  | BILL/01919/2023-2024 | 93 | 13/07/2023 | 13/07/2023 | WBSEDCL | 11.28 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Quotation for New Service Connection of Ramnagar W/s Scheme, PH No-II, District-Hooghly Under Electrical Division PHE Dte |  |  | BILL/01920/2023-2024 | 94 | 13/07/2023 | 13/07/2023 | WBSEDCL | 10.9 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Quotation of New Service Connection for Ramnagar w/s Scheme,PH No-3,Block-Arambag,Dist-Hooghly under Electrical Division, PHE Dte |  |  | BILL/04078/2023-2024 | 346 | 11/10/2023 | 11/10/2023 | WBSEDCL | 12.88 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Quotation Bill for for New Service Connection at Salepue Paschimpara Ramnagar W/S. Sch. TW-3 |  |  | BILL/04316/2023-2024 | 428 | 17/11/2023 | 17/11/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RAMNAGAR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000537/2023-2024 | 3088/HUG | 12/10/2023 | 14/04/2025 | UNIQUE AGENCY | 34.81 | 23.65 | 67.93 | 45
9 | HOOGHLY | Arambag | Electrical | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ramnagar water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000054/2023-2024 | 1798/ED | 24/04/2023 | 23/07/2023 | C.M. ENTERPRISE | 21.38 | 21.33 | 99.8 | 50
10 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 21.43 | 100
11 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | RAMNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAG Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000148/2023-2024 | 1503/HUG | 22/05/2023 | 16/03/2025 | UNIQUE AGENCY | 562.52 | 529.38 | 94.11 | 85
12 | HOOGHLY | Arambag | Hooghly Division | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Laying Additional pipeline for connection of 3rd Tubewell with HDPE PE 80, PN 1.0 pipes with supporting structure, Horizontal Auger boring with water jet system and Approach Road at Ramnagar Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000318/2024-2025 | 3688/HUG | 14/11/2024 | 16/04/2025 | UNIQUE AGENCY | 28.47 | 0 | 0 | 50
13 | HOOGHLY | Arambag | Electrical | Ramnagar Piped Water Supply Scheme. | SM/16757 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ramnagar water supply scheme, T.W. No. III, Block: Arambag, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001384/2023-2024 | 4734/ED | 15/12/2023 | 07/05/2024 | H.K.DAS & CO. | 10.76 | 10.4 | 96.64 | 30
Total | [13 empty] | 752.47 | 584.97 | 77.74