## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba-Dadpur | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16763 | New | Material Requisition To Resource Division |  |  | RTOR000229/2023-2024 | 1386/8/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 3.33 | 0 | 0 | 0
2 | HOOGHLY | Polba-Dadpur | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16763 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1264/10/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 9.67 | 0 | 0 | 0
3 | HOOGHLY | Polba-Dadpur | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16763 | New | Material Requisition To Resource Division |  |  | RTOR000502/2023-2024 | 3059/16/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 3.33 | 0 | 0 | 0
4 | HOOGHLY | Polba-Dadpur | Electrical | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16763 | New | Quotation Bill for New Service Connection at Basta W/S. Sch.TW-I |  |  | BILL/04580/2023-2024 | 578 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.06 | 0 | 0 | 0
5 | HOOGHLY | Polba-Dadpur | Electrical | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16763 | New | Quotation Bill for New Service Connection at Basta W/S. Sch. TW-II |  |  | BILL/05115/2023-2024 | 686 | 19/01/2024 | 19/01/2024 | WBSEDCL | 3.61 | 0 | 0 | 0
6 | HOOGHLY | Polba-Dadpur | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16763 | New | BASTA Piped Water Supply Scheme with Sinking of tube-well, Laying Distrubtuion System, Rising Main, Providing FHTC, construction of switch-rooms & boundary walls at different TW site under Hooghly Division, PHE Dte. within POLBA-DADPUR Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000780/2022-2023 | 844/HUG | 23/03/2023 | 01/10/2025 | TOTON MONDAL | 142.86 | 81.67 | 57.16 | 60
Total | [13 empty] | 165.87 | 81.67 | 49.23