## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 1383/25/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.09 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1235/12/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 58.83 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Quotation Bill for New Service Connection at Mahishtikri W/S. Sch. TW-I, Z-I |  |  | BILL/04168/2023-2024 | 407 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.04 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Quotation Bill for New Service Connection at Mahishtikari W/S. Sch. TW-II, Z-I |  |  | BILL/04167/2023-2024 | 406 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.91 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-I) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000042/2023-2024 | 1728/ED | 19/04/2023 | 01/09/2025 | MENAKA ENTERPRISE | 20.26 | 19.47 | 96.09 | 30
6 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | MAHISHTIKRI ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Haripal Block junior Enginner,Junior Engineer (Civill) | ORD/000195/2023-2024 | 1786/HUG | 16/06/2023 | 17/04/2025 | MAA TARA CONSTRUCTION | 266.67 | 159.2 | 59.7 | 100
7 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Route Survey for Augmentation of Mahistikri Zone - I Piped Water Supply Scheme under Chandannagar Sub Division, PHE Dte.[Part-A] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000431/2025-2026 | 1018/Chan | 30/07/2025 | 14/08/2025 | APEX ENGINEERING | 0.73 | 0 | 0 | 100
8 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Preparation of CAD-GIS Drawing and Pipe Network Design for Augmentation of Mahistikri Zone - I Piped Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000429/2025-2026 | 1016/Chan | 30/07/2025 | 14/08/2025 | APEX ENGINEERING | 0.84 | 0 | 0 | 100
9 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Route Survey for Augmentation of Mahistikri Zone - I Piped Water Supply Scheme under Chandannagar Sub Division, PHe Dte. [Part-B] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000432/2025-2026 | 1019/Chan | 30/07/2025 | 14/08/2025 | APEX ENGINEERING | 0.95 | 0 | 0 | 100
10 | HOOGHLY | Haripal | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | SM/16979 | New | Preparation of DPR for Augmentation of Mahistikri Zone - I Piped Water Supply Scheme under Chandannagar Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000430/2025-2026 | 1017/Chan | 30/07/2025 | 14/08/2025 | APEX ENGINEERING | 0.78 | 0 | 0 | 100
Total | [13 empty] | 361.09 | 178.67 | 49.48