## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-II | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | Material Requisition To Resource Division |  |  | RTOR000318/2023-2024 | 1384/15/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 4.88 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-II | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | Material Requisition To Resource Division |  |  | RTOR000548/2023-2024 | 3060/7/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 4.88 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-II | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | Material Requisition To Resource Division |  |  | RTOR000340/2023-2024 | 3005/13/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 4.88 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-II | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JAGANNATHBATI HW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000149/2024-2025 | 432/SER | 31/07/2024 | 15/08/2024 | SRI KRISHNA ENTERPRISE | 0.36 | 0 | 0 | 95
5 | HOOGHLY | Chanditala-II | Electrical | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004146914 Reference ID- 503632742 SM Code- 17176 |  |  | BILL/00437/2024-2025 | 128 | 17/05/2024 | 17/05/2024 | WBSEDCL | 3.91 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-II | Electrical | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004146792 Reference ID- 503632743 SM Code- 17176 |  |  | BILL/00444/2024-2025 | 133 | 17/05/2024 | 17/05/2024 | WBSEDCL | 9.39 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-II | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | JAGANNATHBATI Piped Water Supply Scheme with Sinking of tubewell, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000012/2023-2024 | 1042/Hug | 10/04/2023 | 01/01/2026 | M/S SHIVAM UDYOG | 212.99 | 0 | 0 | 30
8 | HOOGHLY | Chanditala-II | Electrical | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | SM/17176 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathbati water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000051/2023-2024 | 1795/ED | 24/04/2023 | 01/07/2025 | AHALYA ENGINEERING WORKS | 20.26 | 0 | 0 | 60
Total | [13 empty] | 261.56 | 0 | 0