## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Material Requisition To Resource Division |  |  | RTOR000264/2022-2023 | 902/2/Hug | 27/03/2023 |  | Resource Division | 10.56 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1235/9/Hug | 28/04/2023 |  | Resource Division | 13.03 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 1383/17/Hug | 15/05/2023 |  | Resource Division | 10.56 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Quotation for new service connection at Boinchipota W/s sch. , T/W - I, Block- Singur, Dist. -hooghly |  |  | BILL/02062/2023-2024 | 110 | 19/07/2023 |  | WBSEDCL | 3.99 | 0 | 0 | 0
5 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Material Requisition To Resource Division |  |  | RTOR000419/2023-2024 | 3058/14/Hug | 11/10/2023 |  | Resource Division | 10.56 | 0 | 0 | 0
6 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Quotation for new service connection at Boinchipota W/S Sch,, Zone - I. T/W No. - II |  |  | BILL/04125/2023-2024 | 382 | 25/10/2023 |  | WBSEDCL | 2.44 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000053/2023-2024 | 1797/ED | 24/04/2023 | 23/07/2023 | MITRA ASSOCIATES | 20.2 | 9.94 | 49.22 | 97
8 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | BAINCHIPOTA (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2023-2024 | 1041/Hug | 10/04/2023 | 05/01/2024 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 491.76 | 179.77 | 36.56 | 20
9 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte. (Baichipota Z-I PWSS, Baichipota Z-II PWSS, Kharda Apurbapur PWSS, Baruipara PWSS, Sripatipur PWSS, Paschim Gopinathpur PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000976/2023-2024 | 304/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.48 | 50 | 100
10 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | SM/17289 | New | Additional Quotation for new service connection at Bainchipota[SM/17289] W/S Sch., Zone - I, T/W No. - II under Nasibpur CCC, WBSEDCL, Ref. Id. - 860298080, Dt. - 23/04/2024, Application ID. - 100000106100 |  |  | BILL/00330/2024-2025 | 98 | 06/05/2024 |  | WBSEDCL | 0.25 | 0 | 0 | null
Total | [13 empty] | 564.3 | 190.19 | 33.7