## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17290 | New | MAHISGOT Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000782/2022-2023 | 861/HUG | 24/03/2023 | 19/12/2023 | M/S R.M. CONSTRUCTION | 221.92 | 69.65 | 31.39 | 15
2 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17290 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mahishgot water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer4 | ORD/000082/2023-2024 | 1999/ED | 19/05/2023 | 01/01/2026 | AMITAVA CHAKRABORTY | 20.29 | 0 | 0 | 30
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17290 | New | Material Requisition To Resource Division |  |  | RTOR000481/2023-2024 | 3057/7/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 4.35 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17290 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1234/18/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 9.11 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17290 | New | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000400/2024-2025 | 3780/HUG | 25/11/2024 | 24/01/2025 | ROY ENTERPRISE | 55.39 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17290 | New | Quotation Bill for New Service Connection at Mahisgot W/S. Sch. PH-I |  |  | BILL/06151/2023-2024 | 794 | 22/02/2024 | 22/02/2024 | WBSEDCL | 20.71 | 0 | 0 | 0
Total | [13 empty] | 331.76 | 69.65 | 20.99