## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 1385/35/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 8.34 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1234/20/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 40.63 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | Material Requisition To Resource Division |  |  | RTOR000437/2023-2024 | 3057/31/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 8.34 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | PURBBA KRISHNAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION, Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000177/2023-2024 | 1682/HUG | 08/06/2023 | 04/03/2024 | M/S R K ENTERPRISE | 442.41 | 71.31 | 16.12 | 10
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-II,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208366 Reference Id-503655425. |  |  | BILL/00671/2024-2025 | 203 | 10/06/2024 | 10/06/2024 | WBSEDCL | 3.71 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-I,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208398 Reference Id-503655423. |  |  | BILL/00672/2024-2025 | 202 | 10/06/2024 | 10/06/2024 | WBSEDCL | 4.86 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17625 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purbba Krishnapur water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000044/2023-2024 | 1730/ED | 19/04/2023 | 01/07/2025 | CINZANO | 20.96 | 0 | 0 | 50
Total | [13 empty] | 529.27 | 71.31 | 13.47