## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1234/32/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 15.57 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 1385/4/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 8.26 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Material Requisition To Resource Division |  |  | RTOR000461/2023-2024 | 3057/20/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 8.26 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of PUKURIA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000375/2024-2025 | 3718/HUG | 19/11/2024 | 17/02/2025 | JOY GURU ENTERPRISE | 16.06 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000403/2024-2025 | 3781/HUG | 25/11/2024 | 24/01/2025 | KAJAL DEY | 55.4 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Quotation of New Service Connection for Pukhuria w/s Scheme,PH No-I,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004294636 Reference Id-503691998 |  |  | BILL/01173/2024-2025 | 313 | 23/07/2024 | 23/07/2024 | WBSEDCL | 4.01 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Quotation of New Service Connection for Pukuria w/s Scheme,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004151686 Reference Id-503633620 |  |  | BILL/00413/2024-2025 | 101 | 05/05/2024 | 05/05/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
8 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pukhuria water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000047/2023-2024 | 1733/ED | 19/04/2023 | 01/01/2026 | B.T. PROJECT PVT. LTD. | 41.11 | 0 | 0 | 10
9 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17626 | New | PUKHURIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000272/2023-2024 | 2290/HUG | 03/08/2023 | 21/10/2025 | M/S R.M. CONSTRUCTION | 360.54 | 68.78 | 19.08 | 10
Total | [13 empty] | 513.35 | 68.78 | 13.4