## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Material Requisition To Resource Division |  |  | RTOR000268/2022-2023 | 902/5/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 15.17 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1235/2/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 69.72 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Material Requisition To Resource Division |  |  | RTOR000275/2023-2024 | 1383/26/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 15.17 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Material Requisition To Resource Division |  |  | RTOR000431/2023-2024 | 3058/13/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.17 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Quotation for new service connection at Nasibpur W/s Sch.,H/W Site(T/W No. - I), Dist. - Hooghly |  |  | BILL/01922/2023-2024 | 89 | 12/07/2023 | 12/07/2023 | WBSEDCL | 3.56 | 0 | 0 | 0
6 | HOOGHLY | Singur | Electrical | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Quotation for new service connection charge at Nasibpur PWSS, TW - II |  |  | BILL/04482/2023-2024 | 527 | 14/12/2023 | 14/12/2023 | WBSEDCL | 0.73 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000043/2023-2024 | 1729/ED | 19/04/2023 | 18/07/2023 | ANIK & CO. | 20.5 | 0 | 0 | 45
8 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000200/2023-2024 | 1804/HUG | 21/06/2023 | 05/08/2023 | OSMAN SEKH | 80.84 | 0 | 0 | 100
9 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of NASIBPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000745/2023-2024 | 384/HUG | 08/02/2024 | 08/04/2024 | M/S ALPHA CONSTRUCTION | 15.5 | 0 | 0 | 100
10 | HOOGHLY | Singur | Electrical | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/002477/2023-2024 | 337/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.36 | 0 | 0 | 100
11 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Nasibpur PWSS, Bhandardaha PWSS, Ganderpukur PWSS, Bighati zone-I PWSS, Gopalnagar PWSS, Bahirkhanda PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000971/2023-2024 | 300/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 100
12 | HOOGHLY | Singur | Electrical | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Quotation for new service connection at Nasibpur water supply Scheme [SM/17627], T/W No. - III, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. Id. - 503584530, Dt. - 07-03-2024, Application No. - 5004050532 |  |  | BILL/06277/2023-2024 | 872 | 13/03/2024 | 13/03/2024 | WBSEDCL | 2.63 | 0 | 0 | 0
13 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | NASIBPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000174/2023-2024 | 1679/HUG | 08/06/2023 | 01/01/2026 | BAPPADITYA BANERJEE | 499.98 | 0 | 0 | 60
14 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR | SM/17627 | New | Horizontal road crossing by trenchless method along CN Road(PWD) for NASIBPUR pwss under Chandannagar Sub Division,Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000241/2024-2025 | 3476/HUG | 04/10/2024 | 04/09/2025 | BAPPADITYA BANERJEE | 56.52 | 0 | 0 | 80
Total | [13 empty] | 806.8 | 0 | 0