## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Material Requisition To Resource Division |  |  | RTOR000267/2022-2023 | 902/4/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 14.2 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1235/3/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 33.96 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Material Requisition To Resource Division |  |  | RTOR000214/2023-2024 | 1383/16/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 3.01 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Quotation New Service Connection for Diara Water Supply Scheme, Block - Singur, Dist - hooghly |  |  | BILL/02761/2023-2024 | 172 | 10/08/2023 | 10/08/2023 | WBSEDCL | 3.96 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Quotation Bill for New Service Connection at Diara W/S. Sch. TW-II |  |  | BILL/05922/2023-2024 | 714 | 29/01/2024 | 29/01/2024 | WBSEDCL | 8.07 | 0 | 0 | 0
6 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | DIARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000173/2023-2024 | 1678/HUG | 08/06/2023 | 01/01/2026 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 451.08 | 180.65 | 40.05 | 60
7 | HOOGHLY | Singur | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Horizontal road crossing by trenchless method across BTC Road (PWD) at yuger more & allied works in Diara pwss under Chandannagar Sub-Division, of Hooghly Division P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000225/2024-2025 | 3433/HUG | 03/10/2024 | 03/09/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 11.39 | 0 | 0 | 80
8 | HOOGHLY | Singur | Electrical | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | SM/17628 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Diara water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/002462/2023-2024 | 324/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 20.85 | 20.58 | 98.68 | 90
Total | [13 empty] | 546.53 | 201.23 | 36.82