## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1235/8/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 23.33 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Material Requisition To Resource Division |  |  | RTOR000417/2023-2024 | 3058/11/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 5.75 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 1383/7/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.75 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000046/2023-2024 | 1732/ED | 19/04/2023 | 18/07/2023 | BINAPANI ENTERPRISE | 20.52 | 0 | 0 | 30
5 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Bainchipota (Zone-2) 1st T/W site & Bainchipota (Zone-2) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2024-2025 | 925/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
6 | HOOGHLY | Singur | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - I, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589159, Dt. - 07-03-2024, Application No. - 5004058510 |  |  | BILL/06275/2023-2024 | 875 | 13/03/2024 | 13/03/2024 | WBSEDCL | 9.63 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - II, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589664, Dt. - 07-03-2024, Application No. - 5004059136 |  |  | BILL/06280/2023-2024 | 874 | 13/03/2024 | 13/03/2024 | WBSEDCL | 0.64 | 0 | 0 | 0
8 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | BAINCHIPOTA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000301/2023-2024 | 2365/HUG | 08/08/2023 | 01/01/2026 | RAJ CONSTRUCTION | 300.28 | 0 | 0 | 60
9 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Bainchipota (Zone-II) Piped Water Supply Scheme under Chandannagar Sub Division under Hooghly Division PHE Dte.(Phase-I) for Singur Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000390/2024-2025 | 963/CHAN | 21/11/2024 | 26/11/2024 | BIMAL KUMAR HALDER | 4.13 | 0 | 0 | 100
10 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Bainchipota (Zone-II) Piped Water Supply Scheme under Chandannagar Sub Division under Hooghly Division PHE Dte.(Phase-II) for Singur Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000391/2024-2025 | 964/CHAN | 21/11/2024 | 26/11/2024 | BIMAL KUMAR HALDER | 4.13 | 0 | 0 | 100
Total | [13 empty] | 375.13 | 0 | 0