## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1235/8/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 23.33 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Material Requisition To Resource Division |  |  | RTOR000417/2023-2024 | 3058/11/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 5.75 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 1383/7/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.75 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000046/2023-2024 | 1732/ED | 19/04/2023 | 18/07/2023 | BINAPANI ENTERPRISE | 20.52 | 0 | 0 | 30
5 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Bainchipota (Zone-2) 1st T/W site & Bainchipota (Zone-2) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2024-2025 | 925/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
6 | HOOGHLY | Singur | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - I, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589159, Dt. - 07-03-2024, Application No. - 5004058510 |  |  | BILL/06275/2023-2024 | 875 | 13/03/2024 | 13/03/2024 | WBSEDCL | 9.63 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - II, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589664, Dt. - 07-03-2024, Application No. - 5004059136 |  |  | BILL/06280/2023-2024 | 874 | 13/03/2024 | 13/03/2024 | WBSEDCL | 0.64 | 0 | 0 | 0
8 | HOOGHLY | Singur | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | SM/17629 | New | BAINCHIPOTA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000301/2023-2024 | 2365/HUG | 08/08/2023 | 01/01/2026 | RAJ CONSTRUCTION | 300.28 | 0 | 0 | 60
Total | [13 empty] | 366.86 | 0 | 0