## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Material Requisition To Resource Division |  |  | RTOR000303/2023-2024 | 1384/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 13.1 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-I | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Material Requisition To Resource Division |  |  | RTOR000475/2023-2024 | 3060/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.43 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-I | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1236/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 25.53 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-I | Electrical | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Quotation money deposition for new service connection at Jogmohanpur w/s scheme, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5003805642 Reference ID- 503409286 SM Code- 17632 |  |  | BILL/01403/2024-2025 | 347 | 31/07/2024 | 31/07/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I | Electrical | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Quotation bill for new service connection charges at Jagmohanpur w/s scheme, P.H. No.-I, Dist: Hooghly. Application No.-5004024656 Ref ID: 503569651 |  |  | BILL/06264/2023-2024 | 863 | 12/03/2024 | 12/03/2024 | WBSEDCL | 7.56 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-I | Electrical | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagmohanpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000052/2023-2024 | 1796/ED | 24/04/2023 | 31/01/2025 | MASSK ENGINEERING WORKS. | 20.35 | 6.65 | 32.65 | 75
7 | HOOGHLY | Chanditala-I | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/17632 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 10/08/2025 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 29.61 | 0.91 | 9
Total | [13 empty] | 3325.4 | 36.26 | 1.09