## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dharmmapur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer3,Junior Engineer4 | ORD/000050/2023-2024 | 1794/ED | 24/04/2023 | 01/08/2025 | M/S, GHOSH ENTERPRISE | 20.35 | 2.89 | 14.2 | 30
2 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | DHARMMAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000005/2023-2024 | 1017/Hug | 06/04/2023 | 26/02/2026 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 407.11 | 113.73 | 27.94 | 50
3 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Material Requisition To Resource Division |  |  | RTOR000478/2023-2024 | 3057/9/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.23 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of DHARMMAPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000294/2024-2025 | 3655/HUG | 13/11/2024 | 11/02/2025 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 16.06 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000400/2024-2025 | 3780/HUG | 25/11/2024 | 24/01/2025 | ROY ENTERPRISE | 55.39 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Quotation of New Service Connection for Dharmmapur w/s Scheme,PH No-I Block-Khanakul-I Dist-Hooghly under ED,PHE Dte(SM/17716) Application No-5004012408 Reference Id-503561211 |  |  | BILL/06050/2023-2024 | 741 | 08/02/2024 | 08/02/2024 | WBSEDCL | 5.64 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Quotation of New Service Connection For Dharmmapur w/s scheme,PH No-II Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte(SM/17716) Application no-5004012404 Reference Id-503561209 |  |  | BILL/06049/2023-2024 | 740 | 08/02/2024 | 08/02/2024 | WBSEDCL | 3.59 | 0 | 0 | 0
Total | [13 empty] | 520.37 | 116.62 | 22.41