## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1234/28/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 18.54 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 1385/41/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.59 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Material Requisition To Resource Division |  |  | RTOR000433/2023-2024 | 3057/33/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 5.59 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 04/05/2024 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Quotation of New Service Connection for Bhur Kunda w/s Scheme,Zone-II,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17719) Application No-5004320081 Reference Id- 503705387 |  |  | BILL/01374/2024-2025 | 339 | 30/07/2024 | 30/07/2024 | WBSEDCL | 4.47 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Quotation of New Service Connection for Bhurkunda w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/17719) Application No-5004034182 Reference Id-503574967 |  |  | BILL/06200/2023-2024 | 811 | 28/02/2024 | 28/02/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 140.7 | 3.31 | 30
8 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | SM/17719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone - II, T.W. No. I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000076/2023-2024 | 1932/ED | 15/05/2023 | 21/03/2025 | BISALAXMI ENTERPRISE | 22.61 | 21.18 | 93.7 | 30
Total | [13 empty] | 4376.47 | 161.89 | 3.7