## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1234/27/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 192.54 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 1385/50/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 17.48 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Material Requisition To Resource Division |  |  | RTOR000458/2023-2024 | 3057/21/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 17.48 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHURKUNDA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000138/2024-2025 | 1164/ED | 14/06/2024 | 12/09/2024 | H.K.DAS & CO. | 10.89 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Quotation of New Service Connection for Bhurkunda w/s scheme, Zone-I,PH No-I Block-Goghat-II,under Electrical Division,PHE Dte.(SM/17721) Application No-5004243748 Reference Id-503669340. |  |  | BILL/00831/2024-2025 | 230 | 20/06/2024 | 20/06/2024 | WBSEDCL | 3.15 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Quotation of New Service Connection for Bhurkunda w/s Scheme, Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17721) Application No-5004190543 Reference Id-503647430. |  |  | BILL/00483/2024-2025 | 149 | 22/05/2024 | 22/05/2024 | WBSEDCL | 3.63 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 155.48 | 3.66 | 30
8 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 22/03/2025 | TECHVISION | 6.59 | 0 | 0 | 0
9 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000049/2023-2024 | 1793/ED | 24/04/2023 | 20/02/2025 | H.K.DAS & CO. | 22.39 | 0 | 0 | 40
Total | [13 empty] | 4525.66 | 155.48 | 3.44