## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1234/27/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 192.54 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 1385/50/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 17.48 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Material Requisition To Resource Division |  |  | RTOR000458/2023-2024 | 3057/21/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 17.48 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHURKUNDA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000138/2024-2025 | 1164/ED | 14/06/2024 | 12/09/2024 | H.K.DAS & CO. | 10.89 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Quotation of New Service Connection for Bhurkunda w/s scheme, Zone-I,PH No-I Block-Goghat-II,under Electrical Division,PHE Dte.(SM/17721) Application No-5004243748 Reference Id-503669340. |  |  | BILL/00831/2024-2025 | 230 | 20/06/2024 | 20/06/2024 | WBSEDCL | 3.15 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Quotation of New Service Connection for Bhurkunda w/s Scheme, Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17721) Application No-5004190543 Reference Id-503647430. |  |  | BILL/00483/2024-2025 | 149 | 22/05/2024 | 22/05/2024 | WBSEDCL | 3.63 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 155.48 | 3.66 | 30
8 | HOOGHLY | Goghat-II | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | SM/17721 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000049/2023-2024 | 1793/ED | 24/04/2023 | 20/02/2025 | H.K.DAS & CO. | 22.39 | 0 | 0 | 40
Total | [13 empty] | 4519.07 | 155.48 | 3.44