## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba-Dadpur | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Material Requisition To Resource Division |  |  | RTOR000263/2023-2024 | 1386/42/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 2.94 | 0 | 0 | 0
2 | HOOGHLY | Polba-Dadpur | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Material Requisition To Resource Division |  |  | RTOR000361/2023-2024 | 3004/14/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 2.71 | 0 | 0 | 0
3 | HOOGHLY | Polba-Dadpur | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Material Requisition To Resource Division |  |  | RTOR000504/2023-2024 | 3059/15/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 2.94 | 0 | 0 | 0
4 | HOOGHLY | Polba-Dadpur | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJHAT UTTAR PROPOSED TW Site under Chirnurah Sub Division, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/002584/2023-2024 | 459/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 7.16 | 73.86 | 90
5 | HOOGHLY | Polba-Dadpur | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Quotation Bill for New Service Connection at Rajhat Dakshinpara W/S. Sch. TW-I |  |  | BILL/04458/2023-2024 | 519 | 11/12/2023 | 11/12/2023 | WBSEDCL | 10.03 | 0 | 0 | 0
6 | HOOGHLY | Polba-Dadpur | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Quotation for new service connection at Rajhat(Uncovered)[Rajhat Uttar] W/S Sch.[SM/18095], T/W No. - I, Mahashay Para, Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599474, Dt. - 22-03-2024, Application No. - 5004078306 |  |  | BILL/00013/2024-2025 | 16 | 04/04/2024 | 04/04/2024 | WBSEDCL | 11.27 | 0 | 0 | 0
7 | HOOGHLY | Polba-Dadpur | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | RAJHAT Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000240/2023-2024 | 2078/HUG | 18/07/2023 | 28/07/2025 | TAPAS ADHYA | 118.43 | 97.58 | 82.39 | 80
8 | HOOGHLY | Polba-Dadpur | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18095 | New | Sinking of tube-well, Rising Main, construction of switch-room & boundary wall at Rajhat Uttar Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000748/2023-2024 | 381/HUG | 08/02/2024 | 28/07/2025 | TAPAS ADHYA | 32.64 | 26.5 | 81.21 | 25
Total | [13 empty] | 190.64 | 131.25 | 68.84