## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | Material Requisition To Resource Division |  |  | RTOR000392/2023-2024 | 3058/10/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 22.67 | 0 | 0 | 0
2 | HOOGHLY | Singur | Electrical | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | Quotation Bill for New Service Connection at Bhandardaha W/S. Sch. TW-I |  |  | BILL/04169/2023-2024 | 408 | 09/11/2023 | 09/11/2023 | WBSEDCL | 2.37 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | BHANDARDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000094/2023-2024 | 1518/HUG | 23/05/2023 | 21/08/2023 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 91.84 | 89.89 | 97.87 | 100
4 | HOOGHLY | Singur | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000001/2024-2025 | 412/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.73 | 0.73 | 100 | 100
5 | HOOGHLY | Singur | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2024-2025 | 413/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
6 | HOOGHLY | Singur | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000003/2024-2025 | 414/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
7 | HOOGHLY | Singur | Electrical | BHANDARDAHA PIPED WATER SUPPLY SCHEME | SM/18096 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhandardaha water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000068/2023-2024 | 1923/ED | 15/05/2023 | 09/05/2024 | ANIK & CO. | 23.07 | 11.23 | 48.69 | 90
Total | [13 empty] | 142.3 | 103.47 | 72.71