## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | KHORDAAPURBAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000180/2023-2024 | 1686/HUG | 08/06/2023 | 06/09/2023 | SATYA NARAYAN BISWAS | 146.57 | 0 | 0 | 60
2 | HOOGHLY | Singur | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Sinking of Additional tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed TW site at kharda-apurbapur Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000065/2024-2025 | 2506/HUG | 03/07/2024 | 17/08/2024 | KALPATARU ENTERPRISE | 37.6 | 0 | 0 | 50
3 | HOOGHLY | Singur | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000008/2024-2025 | 421/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.84 | 0 | 0 | 100
4 | HOOGHLY | Singur | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000007/2024-2025 | 420/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.73 | 0 | 0 | 100
5 | HOOGHLY | Singur | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000009/2024-2025 | 422/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.78 | 0 | 0 | 100
6 | HOOGHLY | Singur | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Khordaapurbapur 1st T/W site & Kamarkundu (Zone-1) 1st T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000292/2024-2025 | 928/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
7 | HOOGHLY | Singur | Electrical | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503675586, dt. - 26-06-2024, Application No. - 5004257575. |  |  | BILL/00978/2024-2025 | 261 | 03/07/2024 | 03/07/2024 | WBSEDCL | 14.47 | 0 | 0 | 0
8 | HOOGHLY | Singur | Electrical | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - II, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503678884, dt. - 26-06-2024, Application No. - 5004264232. |  |  | BILL/00977/2024-2025 | 260 | 03/07/2024 | 03/07/2024 | WBSEDCL | 13.18 | 0 | 0 | 0
9 | HOOGHLY | Singur | Electrical | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | SM/18097 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Khordaa purbapur water supply scheme, T.W. No. I, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000072/2023-2024 | 1928/ED | 15/05/2023 | 28/02/2025 | TAMAL ENTERPRISE | 11.65 | 0 | 0 | 50
Total | [13 empty] | 226.79 | 0 | 0