## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba - Dadpur | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Material Requisition To Resource Division |  |  | RTOR000256/2023-2024 | 1386/35/Hug | 15/05/2023 |  | Resource Division | 4.56 | 0 | 0 | 0
2 | HOOGHLY | Polba - Dadpur | Electrical | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01120/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 104.27 | 0 | 0 | 0
3 | HOOGHLY | Polba - Dadpur | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Material Requisition To Resource Division |  |  | RTOR000363/2023-2024 | 3004/11/Hug | 05/10/2023 |  | Resource Division | 2.71 | 0 | 0 | 0
4 | HOOGHLY | Polba - Dadpur | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Material Requisition To Resource Division |  |  | RTOR000518/2023-2024 | 3059/40/Hug | 11/10/2023 |  | Resource Division | 4.56 | 0 | 0 | 0
5 | HOOGHLY | Polba - Dadpur | Electrical | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Quotation for new service connection charge at Bhatua PWSS, TW - I |  |  | BILL/04370/2023-2024 | 455 | 01/12/2023 |  | WBSEDCL | 15.6 | 0 | 0 | 0
6 | HOOGHLY | Polba - Dadpur | Electrical | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Quotation for new service connection charge at Bhatua PWSS, TW - I |  |  | BILL/04370/2023-2024 | 455 | 01/12/2023 |  | WBSEDCL | 15.6 | 0 | 0 | 0
7 | HOOGHLY | Polba - Dadpur | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Ghatampur PWSS 2. Kanajoli PWSS 3. Bhatua PWSS 4. Shrirampur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000777/2023-2024 | 143/CH | 20/02/2024 | 27/02/2024 | MAA BUNAMATA ENTERPRISE | 0.79 | 0.4 | 50 | 30
8 | HOOGHLY | Polba - Dadpur | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | BHATUA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000242/2023-2024 | 2097/HUG | 19/07/2023 | 17/10/2023 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 95.59 | 34.5 | 36.1 | 8
9 | HOOGHLY | Polba - Dadpur | Electrical | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18098 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhatua water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000078/2023-2024 | 1924/ED | 15/05/2023 | 13/08/2023 | UNITED ENTERPRISE | 23.21 | 0 | 0 | 50
Total | [13 empty] | 266.89 | 34.9 | 13.08