## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba - Dadpur | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 1386/4/Hug | 15/05/2023 |  | Resource Division | 3.22 | 0 | 0 | 0
2 | HOOGHLY | Polba - Dadpur | Electrical | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01120/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 104.27 | 0 | 0 | 0
3 | HOOGHLY | Polba - Dadpur | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | Material Requisition To Resource Division |  |  | RTOR000365/2023-2024 | 3004/13/Hug | 05/10/2023 |  | Resource Division | 2.71 | 0 | 0 | 0
4 | HOOGHLY | Polba - Dadpur | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | Material Requisition To Resource Division |  |  | RTOR000526/2023-2024 | 3059/8/Hug | 11/10/2023 |  | Resource Division | 3.22 | 0 | 0 | 0
5 | HOOGHLY | Polba - Dadpur | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | KALORA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000243/2023-2024 | 2098/HUG | 19/07/2023 | 17/10/2023 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 98.59 | 9.04 | 9.17 | 20
6 | HOOGHLY | Polba - Dadpur | Electrical | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | Quotation for new service connection at Kalora W/S Sch.,Near Majhar, [SM/18099], T/W No. - I, Block - Polba-Dadpur under Bandel CCC, WBSEDCL |  |  | BILL/06246/2023-2024 | 850 | 07/03/2024 |  | WBSEDCL | 10.7 | 0 | 0 | null
7 | HOOGHLY | Polba - Dadpur | Electrical | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | SM/18099 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalora water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000071/2023-2024 | 1927/ED | 15/05/2023 | 13/08/2023 | MAA KALI ENTERPRISE | 22.96 | 5.6 | 24.37 | 50
Total | [13 empty] | 245.65 | 14.63 | 5.96