## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Electrical | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalachhara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000070/2023-2024 | 1926/ED | 15/05/2023 | 13/08/2023 | S.G. TECHNICAL SERVICES | 22.6 | 10.77 | 47.65 | 25
2 | HOOGHLY | Haripal | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | KALACHHARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000132/2023-2024 | 1484/HUG | 19/05/2023 | 17/07/2024 | CONCORD PROJECTS PRIVATE LIMITED | 82.76 | 79.78 | 96.39 | 15
3 | HOOGHLY | Haripal | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 1383/8/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.8 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Electrical | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002470/2023-2024 | 331/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 20.85 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000004/2024-2025 | 416/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.93 | 0.93 | 100 | 100
6 | HOOGHLY | Haripal | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000006/2024-2025 | 419/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
7 | HOOGHLY | Haripal | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000005/2024-2025 | 417/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
8 | HOOGHLY | Haripal | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Rajballavbati PWSS, Kalachara PWSS, Paschim Narayanpur PWSS, Mahistikari Z-I PWSS, Mahistikari Z-II PWSS, Parjana PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000977/2023-2024 | 305/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
9 | HOOGHLY | Haripal | Electrical | KALACHHARA PIPED WATER SUPPLY SCHEME | SM/18100 | New | Quotation for New Service Connection at Kalachara W/S. Sch. TW-I |  |  | BILL/04668/2023-2024 | 649 | 10/01/2024 | 10/01/2024 | WBSEDCL | 1.47 | 0 | 0 | 0
Total | [13 empty] | 132.99 | 94.05 | 70.72