## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | SM/18101 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balidaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000067/2023-2024 | 1922/ED | 15/05/2023 | 13/08/2023 | D. K. ELECTRIC | 22.6 | 11.01 | 48.71 | 50
2 | HOOGHLY | Dhaniakhali | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | SM/18101 | New | BALIDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block DHANIAKHALI, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2023-2024 | 1363/HUG | 12/05/2023 | 10/08/2023 | MA KANKALI ENTERPRISE | 85.78 | 85.65 | 99.85 | 92
3 | HOOGHLY | Dhaniakhali | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | SM/18101 | New | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 1386/43/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 2.02 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | SM/18101 | New | Material Requisition To Resource Division |  |  | RTOR000362/2023-2024 | 3004/16/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 14.45 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | SM/18101 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Chautara PWSS 2. Hasnan PWSS 3. Bhatua PWSS 4. Balidaha PWSS 5. Dalimba PWSS 6. Simla PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000776/2023-2024 | 142/CH | 20/02/2024 | 27/02/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 30
6 | HOOGHLY | Dhaniakhali | Electrical | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | SM/18101 | New | Quotation Bill for New Service Connection at Balidaha W/S. Sch. TW-I |  |  | BILL/05064/2023-2024 | 682 | 19/01/2024 | 19/01/2024 | WBSEDCL | 3.71 | 0 | 0 | 0
Total | [13 empty] | 129.51 | 97.62 | 75.37