## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | SM/18102 | New | Material Requisition To Resource Division |  |  | RTOR000265/2023-2024 | 1386/44/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.59 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Electrical | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | SM/18102 | New | Quotation Bill for New Service Connection at Basa Mallikpur mini piped W/S. Sch. |  |  | BILL/04337/2023-2024 | 452 | 29/11/2023 | 29/11/2023 | WBSEDCL | 0.32 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | SM/18102 | New | Ground Water based BARAMALLIKPUR Piped Water Supply Scheme in Dhaniakhali Block under Chinsurah Sub-Division P.H.E. Dte. District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000097/2023-2024 | 1364/HUG | 12/05/2023 | 10/08/2023 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.69 | 0 | 0 | 98
4 | HOOGHLY | Dhaniakhali | Electrical | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | SM/18102 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bara Mallikpur Mini Piped W/S Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/001696/2023-2024 | 5175/ED | 28/12/2023 | 27/03/2024 | RISHAV ENTERPRISE | 7.25 | 0 | 0 | 55
5 | HOOGHLY | Dhaniakhali | Hooghly Division | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | SM/18102 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Uttar HazipurMini PWSS 2. Bara Mallikpur Mini PWSS 3. Sripala Mini PWSS 4. Alasin Mini PWSS 5. Chautpur Mini PWSS 6. Jangalpur Mini PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000998/2023-2024 | 272/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 100
Total | [13 empty] | 41.81 | 0 | 0