## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 1383/45/Hug | 15/05/2023 |  | Resource Division | 1.42 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | SINHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000152/2023-2024 | 1566/HUG | 29/05/2023 | 27/08/2023 | BIMAL KUMAR HALDER | 79.42 | 0 | 0 | 0
3 | HOOGHLY | Singur | Electrical | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01120/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 104.27 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Material Requisition To Resource Division |  |  | RTOR000451/2023-2024 | 3058/7/Hug | 11/10/2023 |  | Resource Division | 1.42 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Quotation for new service connection at Sinhal Patan water supply Scheme [SM/18103], T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. No. - 503588851, Dt. - 07-03-2024, Application No. - 5004057413 |  |  | BILL/06279/2023-2024 | 877 | 13/03/2024 |  | WBSEDCL | 3.3 | 0 | 0 | null
6 | HOOGHLY | Singur | Electrical | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Quotation for new service connection at Sinhal Patan water supply Scheme [SM/18103], T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. No. - 503588851, Dt. - 07-03-2024, Application No. - 5004057413 |  |  | BILL/06279/2023-2024 | 877 | 13/03/2024 |  | WBSEDCL | 3.3 | 0 | 0 | null
7 | HOOGHLY | Singur | Electrical | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sinhal Patnan water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000075/2023-2024 | 1931/ED | 15/05/2023 | 13/08/2023 | H.K.DAS & CO. | 22.34 | 4.28 | 19.14 | 30
8 | HOOGHLY | Singur | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2024-2025 | 429/chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.84 | 0 | 0 | 100
9 | HOOGHLY | Singur | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000012/2024-2025 | 430/chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.78 | 0 | 0 | 100
10 | HOOGHLY | Singur | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME | SM/18103 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000010/2024-2025 | 428/Chan | 09/04/2024 | 24/04/2024 | ENVIROTECH SOLUTIONS | 0.92 | 0 | 0 | 100
Total | [13 empty] | 217.99 | 4.28 | 1.96