## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Material Requisition To Resource Division |  |  | RTOR000315/2023-2024 | 1384/12/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.49 | 0 | 0 | 0
2 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Material Requisition To Resource Division |  |  | RTOR000499/2023-2024 | 3060/9/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 5.49 | 0 | 0 | 0
3 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1236/3/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 5.49 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Bilaspur-I PWSS 2. Bilaspur-II PWSS 3. Hijli PWSS 4. Jaganathpur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000945/2023-2024 | 115/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.64 | 0.64 | 100 | 80
5 | HOOGHLY | Jangipara | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Quotation Bill for New Service Connection at Hijali W/S. Sch. |  |  | BILL/04588/2023-2024 | 595 | 29/12/2023 | 29/12/2023 | WBSEDCL | 6.03 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Quotation Bill for New Service Connection at Hijali W/S. Sch. PH-I |  |  | BILL/04648/2023-2024 | 633 | 08/01/2024 | 08/01/2024 | WBSEDCL | 3.59 | 0 | 0 | 0
7 | HOOGHLY | Jangipara | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Shifting of 11KV HTOH line at Hijali pump house No.-1 Application ID: 100000103017 Ref ID: 860295257 |  |  | BILL/06502/2023-2024 | 899 | 19/03/2024 | 19/03/2024 | WBSEDCL | 6.79 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | HIJALI Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Jangipara Block Junior Engineer (Civill) | ORD/000265/2023-2024 | 2239/HUG | 01/08/2023 | 22/02/2025 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 350.15 | 145.76 | 41.63 | 10
9 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Construction of Shed on open terrace of Existing Laboratory building at Headwork site of Jangipara Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Block- Jangipara). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000024/2025-2026 | 267/SER | 03/04/2025 | 13/04/2025 | MAA TARA CONSTRUCTION | 4.93 | 0 | 0 | 0
10 | HOOGHLY | Jangipara | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & other works at Chandrahati mouza of HIJALI Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000032/2025-2026 | 1055/HUG | 24/04/2025 | 23/06/2025 | R.K. TRADERS | 27.87 | 0 | 0 | 0
11 | HOOGHLY | Jangipara | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18104 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hijali water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000069/2023-2024 | 1925/ED | 15/05/2023 | 01/05/2026 | GLACIER ENGINEERING CO. | 23.4 | 21 | 89.72 | 25
Total | [13 empty] | 439.85 | 167.39 | 38.06