## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Material Requisition To Resource Division |  |  | RTOR000310/2023-2024 | 1384/7/Hug | 16/05/2023 | 16/05/2023 | Resource Division | 7.93 | 0 | 0 | 0
2 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Material Requisition To Resource Division |  |  | RTOR000510/2023-2024 | 3060/8/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 7.93 | 0 | 0 | 0
3 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1236/4/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 32.71 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Material Requisition To Resource Division |  |  | RTOR000349/2023-2024 | 3005/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 0.01 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mundalika-I PWSS 2. Mundalika-II PWSS 3. Nilarpur PWSS 4. Gopalpur PWSS 5. Bishnupur PWSS 6. Radhanagar PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000944/2023-2024 | 114/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
6 | HOOGHLY | Jangipara | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. |  |  | BILL/04635/2023-2024 | 635 | 08/01/2024 | 08/01/2024 | WBSEDCL | 4.83 | 0 | 0 | 0
7 | HOOGHLY | Jangipara | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. PH-I |  |  | BILL/04638/2023-2024 | 634 | 08/01/2024 | 08/01/2024 | WBSEDCL | 8.22 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | NILARPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000230/2023-2024 | 2063/HUG | 17/07/2023 | 28/09/2026 | BANSBERIA CONSTRUCTION CO. | 411.87 | 170.81 | 41.47 | 40
9 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Repairing of Damaged Road due to FHTC Works at Tara & Kumar Bazar mouzas of Antpur mouza under Nilarpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000195/2024-2025 | 538/SER | 17/09/2024 | 24/09/2024 | SUNITI MAIRA | 4.96 | 0 | 0 | 99
10 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Providing Functional House Hold Tap Connection (FHTC) within left out habitation of various Mouzas in Antpur mouza under Nilarpur Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000196/2024-2025 | 541/SER | 19/09/2024 | 01/04/2025 | SURAJIT SINGHA RAY | 4.99 | 0 | 0 | 99
11 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Laying Additional Pipeline within left out habitation of various Mouzas in Antpur mouza under Nilarpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000197/2024-2025 | 542/SER | 19/09/2024 | 01/01/2025 | SURAJIT SINGHA RAY | 4.89 | 0 | 0 | 99
Total | [13 empty] | 489.3 | 171.76 | 35.1