## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block | SM/18107 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DANTRA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000193/2023-2024 | 1776/HUG | 15/06/2023 | 30/07/2023 | VAIDIK CONSTRUCTION | 11.42 | 0 | 0 | 70
Total | [13 empty] | 11.42 | 0 | 0