## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block | SM/18108 | Retrofitting | 2nd Continuation of Maintenance of Laying Distribution System including Street Stand post, Rising main & other essential components of Chopa, Gopinagar, Dantra, Hassampore, Dighir W/S Scheme for the period from 01/07/2023 to 31/07 /2023 under Chinsurah Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000234/2023-2024 | 562/CH | 27/06/2023 | 28/07/2023 | BOSE ENTERPRISE (RATUL BOSE) | 0.79 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block | SM/18108 | Retrofitting | 1st Continuation of Maintenance of Laying Distribution System including Street Stand post, Rising main & other essential components of Chopa, Gopinagar, Dantra, Hassampore, Dighir W/S Scheme for the period from 01/06/2023 to 30/06 /2023 under Chinsurah Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000233/2023-2024 | 459/CH | 29/05/2023 | 28/06/2023 | BOSE ENTERPRISE (RATUL BOSE) | 0.77 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block | SM/18108 | Retrofitting | 3RD Continuation of Maintenance of Laying Distribution System including Street Stand post, Rising main & other essential components of Chopa, Gopinagar, Dantra, Hassampore, Dighir W/S Scheme for the period from 01/08/2023 to 31/08 /2023 under Chinsurah Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000575/2023-2024 | 713/CH | 28/07/2023 | 28/08/2023 | BOSE ENTERPRISE (RATUL BOSE) | 0.79 | 0 | 0 | 0
Total | [13 empty] | 2.35 | 0 | 0