## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block | SM/18109 | Retrofitting | Providing FHTC in rest out portion of at Radhanagar of Gopinagar PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001048/2023-2024 | 292/CH | 15/03/2024 | 22/03/2024 | RAJMAHAL ENTERPRISE | 0.99 | 0.93 | 94.36 | 100
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block | SM/18109 | Retrofitting | Providing FHTC in rest out portion of at Gopinagar of Gopinagar PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001047/2023-2024 | 291/CH | 15/03/2024 | 22/03/2024 | RAJMAHAL ENTERPRISE | 0.99 | 0.93 | 94.36 | 100
Total | [13 empty] | 1.98 | 1.87 | 94.36