## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Laying of rising main for Interconnection of Laying Distribution System & 7 th Tubewell Including Protection Work of BARUIPARA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000388/2022-2023 | 2141/HUG | 26/09/2022 | 16/10/2022 | AMBIAN INFRASTRUTTURE | 5.97 | 5.96 | 99.94 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BARUIPARA PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000344/2023-2024 | 2433/HUG | 11/08/2023 | 09/11/2023 | MALLIKA ENTERPRISE | 95.97 | 65.29 | 68.04 | 50
Total | [13 empty] | 101.93 | 71.26 | 69.9