## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Laying of rising main for Interconnection of Laying Distribution System & 7 th Tubewell Including Protection Work of BARUIPARA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000388/2022-2023 | 2141/HUG | 26/09/2022 | 16/10/2022 | AMBIAN INFRASTRUTTURE | 5.97 | 5.96 | 99.94 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BARUIPARA PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000344/2023-2024 | 2433/HUG | 11/08/2023 | 09/11/2023 | MALLIKA ENTERPRISE | 95.97 | 95.95 | 99.98 | 50
3 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of BARUIPARA PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000479/2024-2025 | 4070/HUG | 19/12/2024 | 19/03/2025 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.04 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Surging/Development of old tubewell using suitable air compressor to increase the yield at different Water Supply Scheme within Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. (Baruipara 5 Tube Well, Bandipur 3rd Tube Well) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000313/2025-2026 | 958/CHAN | 23/07/2025 | 07/08/2025 | G. T. AGRO CENTRE | 1.47 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | SM/18110 | Retrofitting | Damage road repairing at different location at mouza Ajabnagar ,Paltaghar and Biramnagar under Baruipara PWSS under Singur block of Chandannagar Sub Division under Hooghly division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002190/2024-2025 | 223/Chan | 20/02/2025 | 12/03/2025 | ASHA ENTERPRISE | 4.98 | 0 | 0 | 100
Total | [13 empty] | 121.42 | 101.92 | 83.94