## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 11/05/2023 | MS D.PALIT AND CO. | 62.24 | 12.32 | 19.79 | 100
2 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in NAWPARA Water Supply Scheme at SINGUR Block under Chandannagar Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000274/2023-2024 | 2294/HUG | 03/08/2023 | 26/09/2025 | DIPTI TRADERS | 757.77 | 598.38 | 78.97 | 87
3 | HOOGHLY | Singur | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawpara water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000810/2023-2024 | 3063/ED | 12/07/2023 | 10/10/2023 | POLYCON ENGINEERS | 21.71 | 21.69 | 99.91 | 92
4 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 06/08/2023 | OSMAN SEKH | 80.85 | 16.41 | 20.3 | 100
5 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Material Requisition To Resource Division |  |  | RTOR000194/2022-2023 | 109/4/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 52 | 0 | 0 | 0
6 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Material Requisition To Resource Division |  |  | RTOR000390/2023-2024 | 3058/6/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 17.71 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Quotation Bill for New Service Connection at Nawpara W/S. Sch. TW-II |  |  | BILL/04503/2023-2024 | 547 | 19/12/2023 | 19/12/2023 | WBSEDCL | 15.9 | 0 | 0 | 0
8 | HOOGHLY | Singur | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Quotation for service connection for Nawpara W/S Sch. , T/W -I, Block - Singur |  |  | BILL/02064/2023-2024 | 111 | 19/07/2023 | 19/07/2023 | WBSEDCL | 2.63 | 0 | 0 | 0
9 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for NAWPARA Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000236/2024-2025 | 3471/HUG | 04/10/2024 | 01/01/2026 | DIPTI TRADERS | 26.55 | 0 | 0 | 60
10 | HOOGHLY | Singur | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | Quotation for new service connetion at Nawpara W/S Sch.[SM/18241], T/W No. - III, Block - Singur, Dt. - Hooghly under Khalisani CCC, WBSEDCL, Ref Id. - 503987286, Dt. - 10-06-2025, Application No. - 5004772265 |  |  | BILL/01104/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 5.46 | 0 | 0 | 0
11 | HOOGHLY | Singur | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME | SM/18241 | New | DAMAGE OF ROAD DURING LYING OF WATER SUPPLY PIPE LINE MAINLY T03 -NOWAPARA MORE (DELHI ROAD) TO MALIKPUR JAMIRBERIA VIA ANANDSANAGAR VIDE PACKAGE NO.WB-08-358 UNDER SINGUR BLOCK IN HOOGHLY DISTRICT. |  |  | BILL/00205/2025-2026 |  | 19/05/2025 | 19/05/2025 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 27.22 | 0 | 0 | 0
Total | [13 empty] | 1070.03 | 648.8 | 60.63